## standard_user
Defect ID | TestCase ID | Defect Summary | Reproduced Step | Test Data | Defect Type | Defect Priority | Defect Severity | Expected Result | Actual Result | Tester Name | Attachment | Status
1 | 2 | check login button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : standard_user Password : secret_sauce | Functionality, security defect | high | high | To open the user dashboard with proper details | As Per Expected Resultbut not to see user detail after Login | Konik | https://drive.google.com/file/d/13RvvFXIEAF_kWiQhoSX18X_QBpRnFmZy/view?usp=sharing | Open
2 | 2 | check login button with blank/null value | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message only show username is required not to show password message | Konik | https://drive.google.com/file/d/1FzXKLYc-8hvQTBwwoLLivPJZ4UjbKh5u/view?usp=drive_link | Open
3 | 2 | check login button with wrong value | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf Password : asdf | Functionality defect | medium | low | To display proper validation message | error message is proper but not to display properly its inside the text box | Konik | https://drive.google.com/file/d/1SQoo1fk0L-puTDA-wkg8_SPS1tulVzoB/view?usp=drive_link | Open
4 | 2 | check login button with username is correct but password is wrong | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : standard_user Password : asdf | Functionality defect | medium | low | To display proper validation message | not to display proper validation message and also not to display proper message insite textbox | Konik | https://drive.google.com/file/d/1DDF8kQXijqPpZP61ARZ7yY2fzv9fAfZF/view?usp=drive_link | Open
5 | 2 | check login button with username is wrong but password is correct | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message and also not to display proper message insite textbox | Konik | https://drive.google.com/file/d/17jWvqmR6cEA_Oa9NH950SK6YDQRyLuZF/view?usp=drive_link | Open
6 | 2 | check login button with proper length in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdfasdfasdfasdfasddaaddaasdf Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1ZNCJPyoGjClp61OfJOH4INx5I2yvn9nG/view?usp=drive_link | Open
7 | 2 | check login button with special character in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf@#$asdf Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1Nf95EL1neOkWW0SHQWZRejUEdHwrT-78/view?usp=drive_link | Open
8 | 2 | check login button with only digit in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : 123456789 Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1NcK2ZCsD3JwOBowD5pWm2iyYQE2z6Wc4/view?usp=drive_link | Open
9 | 2 | check login button with using white space in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : k o n I k Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/115k4AxMdRkE2wH6n_heFftNNln2_u9I4/view?usp=drive_link | Open
10 | 2 | check login button with using white space after and before username in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : k o n I k Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1_awOj68lt5b-MssOjODTqkeKKErbm1Ym/view?usp=drive_link | Open
11 | 2 | check login button with using white space after and before password in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1T4X8txUkmX_v3ELB_3-wPRDCq54FQmIY/view?usp=drive_link | Open
12 | 2 | check login button with max length of username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konikkonikkonikkonik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1NyR4DWFvGFy6T9H84i_MTlmTA78CoBjf/view?usp=drive_link | Open
13 | 2 | check login button with not to same username in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1J0Pek56bkOemxIjwNe-1wRYCnBQtp0Wu/view?usp=drive_link | Open
14 | 2 | check login button with uppercase in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : Konik Password : KONIK | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1Y8WgTcHH9hWTRWPN2TFlsG3wvBWCWSTZ/view?usp=drive_link | Open
15 | 2 | check login button with lowercase in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1p2sSqICQ4-if-cmhQwUDT2IDTYa6YzQD/view?usp=drive_link | Open
16 | 2 | check login button with one digit in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK2711 | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1DBfB4oUJGjK1vHAh10Pwtv-nMGl-gPIW/view?usp=drive_link | Open
17 | 2 | check login button with one special character in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK@2711 | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1yRwA579SGCvbW45FpeT3hNcYi3czrltK/view?usp=drive_link | Open
18 | 4 | check all item menu | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) check side menu 5) click allitems menu | Na | Functionality defect | medium | medium | To open items page | no to do anything upon that | Konik | https://drive.google.com/file/d/1iqtnxSDzGr8ZcBTnZzTfgiUYJ0gdwmGW/view?usp=drive_link | Open
19 | 5 | check about menu | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) check side menu 5) click about menu | Na | Functionality defect | low | low | To open the about page | to open another website (https://app.eu-central-1.saucelabs.com) | Konik | https://drive.google.com/file/d/12r0bHx2C91B4_plnk-IxQISiJW5p8zRq/view?usp=drive_link | Open
20 | 6 | check reset app state | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) check side menu 5) click Reset app state | Na | Functionality defect | low | low | To open the reset app state page | no to do anything upon that | Konik | https://drive.google.com/file/d/1IFWUUKqQHXLy14enkVSJcYxPPcNDhYLF/view?usp=drive_link | Open
21 | 19 | check checkout information menu with no first name, no last name, no zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for first name) | Konik | https://drive.google.com/file/d/1SAmjWmzGZuZV23sUDZ5vNHxGzFZfcTow/view?usp=drive_link | Open
22 | 19 | check checkout information menu with first name, no last name, no zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for last name) | Konik | https://drive.google.com/file/d/1qbJFOquJe6HS1dXAcOyb0-OgcEMu6Qts/view?usp=drive_link | Open
23 | 19 | check checkout information menu with no first name, only last name, no zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for first name) | Konik | https://drive.google.com/file/d/1b6P54TMybWJA8ECp2yzl2Uei48j1uCmg/view?usp=drive_link | Open
24 | 19 | check checkout information menu with no first name, no last name, zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for first name) | Konik | https://drive.google.com/file/d/1VFTl9T5AIyWQqVEdQu2Z8PqX-_WWL5PO/view?usp=drive_link | Open

## Locked_out_user
Defect ID | TestCase ID | Defect Summary | Reproduced Step | Test Data | Defect Type | Defect Priority | Defect Severity | Expected Result | Actual Result | Tester Name | Attachment | Status
1 | 2 | check login button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : locked_out_user Password : secret_sauce | Functionality, security defect | high | high | not to open page due to user already locked out | As Per Expected Result | Konik | https://drive.google.com/file/d/1lEGJthW3DMAuwMWzwtL5bIhWxwOZDAHt/view?usp=drive_link | Open
2 | 2 | check login button with blank/null value | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message only show username is required not to show password message | Konik | https://drive.google.com/file/d/1z6TsNYCVsgr0RVHbCEsRCpYUongGASWv/view?usp=drive_link | Open
3 | 2 | check login button with wrong value | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf Password : asdf | Functionality defect | medium | low | To display proper validation message | error message is proper but not to display properly its inside the text box | Konik | https://drive.google.com/file/d/1eNZzLbcCjSsMGxak9VfURNz2h6qsjf2k/view?usp=drive_link | Open
4 | 2 | check login button with username is correct but password is wrong | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : standard_user Password : asdf | Functionality defect | medium | low | To display proper validation message | not to display proper validation message and also not to display proper message insite textbox | Konik | https://drive.google.com/file/d/1oQ4XBBwzBS3_IEgxl-nO31mg_pCnaaW2/view?usp=drive_link | Open
5 | 2 | check login button with username is wrong but password is correct | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message and also not to display proper message insite textbox | Konik | https://drive.google.com/file/d/15nyxjs0KcGmkA9N5vGczZxxENkH2jzG0/view?usp=drive_link | Open
6 | 2 | check login button with proper length in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdfasdfasdfasdfasddaaddaasdf Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1ZE2KBGQMVLEe--bJpqj1HOHOmz0SI4Br/view?usp=drive_link | Open
7 | 2 | check login button with special character in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf@#$asdf Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/12cQUBdHpGNti3B3d5OZy7hoigZoV6KJs/view?usp=drive_link | Open
8 | 2 | check login button with only digit in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : 123456789 Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1BVI0CF-5TiTOAo5I-wAE6Y6VWVB57x8T/view?usp=drive_link | Open
9 | 2 | check login button with using white space in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : k o n I k Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1dLLInv5V0U0fgNp57FSj1-hzdKdOBUUH/view?usp=drive_link | Open
10 | 2 | check login button with using white space after and before username in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : k o n I k Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1xOQYCLNovI8cLuuEj4wwNQ5xTkfPqvBO/view?usp=drive_link | Open
11 | 2 | check login button with using white space after and before password in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1rq77rf8ZTjKU7d-58Jke2a3qsjkt8ei5/view?usp=drive_link | Open
12 | 2 | check login button with max length of username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konikkonikkonikkonik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1eTgy1oa436LYJNZZhLXSbxhJa1_KErsn/view?usp=drive_link | Open
13 | 2 | check login button with not to same username in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1jXgL0VC4bg3IoTlYnTxTZArdRFesHtIV/view?usp=drive_link | Open
14 | 2 | check login button with uppercase in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : Konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1XpbwUSg8QkkUFQHupTcgZOiq98lhmdpP/view?usp=drive_link | Open
15 | 2 | check login button with lowercase in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1XH9VRpOaxRc4T-96eNHcjiMBgLSIcyVi/view?usp=drive_link | Open
16 | 2 | check login button with one digit in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK2711 | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1I2-XGZhy6CWHrM7e34UqLKdv9RtovAcX/view?usp=drive_link | Open
17 | 2 | check login button with one special character in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK@2711 | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/12ejSQBgAaWwsjFfkZ0reAy9s8fi7GJPH/view?usp=drive_link | Open

## problem_user
Defect ID | TestCase ID | Defect Summary | Reproduced Step | Test Data | Defect Type | Defect Priority | Defect Severity | Expected Result | Actual Result | Tester Name | Attachment | Status
1 | 2 | check login button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : problem_user Password : secret_sauce | Functionality, security defect | high | high | To open the user dashboard with proper details | As Per Expected Resultbut not to see user detail after Login | Konik | https://drive.google.com/file/d/13RvvFXIEAF_kWiQhoSX18X_QBpRnFmZy/view?usp=drive_link | Open
2 | 2 | check login button with blank/null value | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message only show username is required not to show password message | Konik | https://drive.google.com/file/d/1FzXKLYc-8hvQTBwwoLLivPJZ4UjbKh5u/view?usp=drive_link | Open
3 | 2 | check login button with wrong value | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf Password : asdf | Functionality defect | medium | low | To display proper validation message | error message is proper but not to display properly its inside the text box | Konik | https://drive.google.com/file/d/1SQoo1fk0L-puTDA-wkg8_SPS1tulVzoB/view?usp=drive_link | Open
4 | 2 | check login button with username is correct but password is wrong | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : problem_user Password : asdf | Functionality defect | medium | low | To display proper validation message | not to display proper validation message and also not to display proper message insite textbox | Konik | https://drive.google.com/file/d/1DDF8kQXijqPpZP61ARZ7yY2fzv9fAfZF/view?usp=drive_link | Open
5 | 2 | check login button with username is wrong but password is correct | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message and also not to display proper message insite textbox | Konik | https://drive.google.com/file/d/17jWvqmR6cEA_Oa9NH950SK6YDQRyLuZF/view?usp=drive_link | Open
6 | 2 | check login button with proper length in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdfasdfasdfasdfasddaaddaasdf Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1ZNCJPyoGjClp61OfJOH4INx5I2yvn9nG/view?usp=drive_link | Open
7 | 2 | check login button with special character in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf@#$asdf Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1Nf95EL1neOkWW0SHQWZRejUEdHwrT-78/view?usp=drive_link | Open
8 | 2 | check login button with only digit in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : 123456789 Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1NcK2ZCsD3JwOBowD5pWm2iyYQE2z6Wc4/view?usp=drive_link | Open
9 | 2 | check login button with using white space in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : k o n I k Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/115k4AxMdRkE2wH6n_heFftNNln2_u9I4/view?usp=drive_link | Open
10 | 2 | check login button with using white space after and before username in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : k o n I k Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1_awOj68lt5b-MssOjODTqkeKKErbm1Ym/view?usp=drive_link | Open
11 | 2 | check login button with using white space after and before password in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1T4X8txUkmX_v3ELB_3-wPRDCq54FQmIY/view?usp=drive_link | Open
12 | 2 | check login button with max length of username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konikkonikkonikkonik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1NyR4DWFvGFy6T9H84i_MTlmTA78CoBjf/view?usp=drive_link | Open
13 | 2 | check login button with not to same username in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1J0Pek56bkOemxIjwNe-1wRYCnBQtp0Wu/view?usp=drive_link | Open
14 | 2 | check login button with uppercase in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : Konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1Y8WgTcHH9hWTRWPN2TFlsG3wvBWCWSTZ/view?usp=drive_link | Open
15 | 2 | check login button with lowercase in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1p2sSqICQ4-if-cmhQwUDT2IDTYa6YzQD/view?usp=drive_link | Open
16 | 2 | check login button with one digit in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK2711 | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1DBfB4oUJGjK1vHAh10Pwtv-nMGl-gPIW/view?usp=drive_link | Open
17 | 2 | check login button with one special character in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK@2711 | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1yRwA579SGCvbW45FpeT3hNcYi3czrltK/view?usp=drive_link | Open
18 | 4 | check all item menu | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) check side menu 5) click allitems menu | Na | Functionality defect | medium | medium | To open items page | no to do anything upon that | Konik | https://drive.google.com/file/d/1SXbKBM_BA0q45a-s-8WMX2q9Ob7D-3GI/view?usp=drive_link | Open
19 | 5 | check about menu | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) check side menu 5) click about menu | Na | Functionality defect | low | low | Not to open the about page | not to open that website shows error page 404 (https://saucelabs.com/error/404) | Konik | https://drive.google.com/file/d/12r0bHx2C91B4_plnk-IxQISiJW5p8zRq/view?usp=drive_link | Open
20 | 6 | check reset app state | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) check side menu 5) click Reset app state | Na | Functionality defect | low | low | To open the reset app state page | no to do anything upon that | Konik | https://drive.google.com/file/d/1rUB62X3h3YWx1vOxvuMVJlgu45W7rADM/view?usp=drive_link | Open
21 | 11 | check image product-1 | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 1 | NA | functionality,user interface defect | high | high | to display another image page | not to display proper image page, open another image with different name (https://www.saucedemo.com/inventory-item.html?id=5) | Konik | https://drive.google.com/file/d/1uXT8NrKypbOqiq-CRqN_shcqXwVlSIug/view?usp=drive_link | Open
22 | 12 | check addtocart button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 1 5) check addto cart button | NA | functionality defect | medium | medium | to add image in addtocart page | to add product in cart from menu page but not to add product inside the image page | Konik | https://drive.google.com/file/d/184AYimlaDXiXtWEZPQzBPj90dnVWDIy1/view?usp=drive_link | Open
23 | 13 | check remove button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 1 5) check remove button | NA | functionality defect | medium | medium | remove image from addtocart page | not remove product from main menu page or inside the image page remove button not shows due to f.id 11 | Konik | https://drive.google.com/file/d/1tZ-iLx40v0AjYTFYDa45RHQyjMi4KncO/view?usp=drive_link | Open
24 | 15 | check image product-2 | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 2 | NA | functionality,user interface defect | high | high | to display another image page | not to display proper image page, open another image with different name (https://www.saucedemo.com/inventory-item.html?id=1) | Konik | https://drive.google.com/file/d/11eQ3bQK3vmZR_nnvtLuzsNIB9IrB2A_q/view?usp=drive_link | Open
25 | 16 | check addtocart button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 2 5) check addto cart button | NA | functionality defect | medium | medium | to add image in addtocart page | to add product in cart from menu page but not to add product inside the image page | Konik | https://drive.google.com/file/d/184AYimlaDXiXtWEZPQzBPj90dnVWDIy1/view?usp=drive_link | Open
26 | 17 | check remove button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 2 5) check remove button | NA | functionality defect | medium | medium | remove image from addtocart menu | not remove product from main menu page or inside the image page remove button not shows due to f.id 15 | Konik | https://drive.google.com/file/d/1tZ-iLx40v0AjYTFYDa45RHQyjMi4KncO/view?usp=drive_link | Open
27 | 19 | check image product-3 | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 3 | NA | functionality,user interface defect | high | high | to display another image page | not to display proper image page, open another image with different name (https://www.saucedemo.com/inventory-item.html?id=2) | Konik | https://drive.google.com/file/d/1YOq0wF_3AUlUsLMDTvc5efg6DTZkrvNd/view?usp=drive_link | Open
28 | 20 | check addtocart button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 3 5) check addto cart button | NA | functionality defect | medium | medium | Not to add image in addtocart page from menu page | not to add product in cart from menu page but add product inside the image page | Konik | https://drive.google.com/file/d/184AYimlaDXiXtWEZPQzBPj90dnVWDIy1/view?usp=drive_link | Open
29 | 21 | check remove button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 3 5) check remove button | NA | functionality defect | medium | medium | remove image from addtocart menu | not remove product from main menu page or inside the image page remove button not working | Konik | https://drive.google.com/file/d/1tZ-iLx40v0AjYTFYDa45RHQyjMi4KncO/view?usp=drive_link | Open
30 | 23 | check image product-4 | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 4 | NA | functionality,user interface defect | high | high | to display an image page | to display item not found page | Konik | https://drive.google.com/file/d/1gSQplbORAuH9EQMdwvdLC8kaRMDTemvd/view?usp=drive_link | Open
31 | 24 | check addtocart button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 4 5) check addto cart button | NA | functionality defect | medium | medium | Not to add image in addtocart page from menu page | not to add product in cart from menu page but add product inside the image page but when we go to the add to cart menu the weblink was down/server fail issue | Konik | Page automatic go to redirect | Open
32 | 25 | check remove button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 4 5) check remove button | NA | functionality defect | medium | medium | remove image from addtocart menu | not remove product from main menu page or inside the image page remove button not working | Konik | https://drive.google.com/file/d/15n04mZhoHbGJRwnBuRk_pxrAtPKFBx8N/view?usp=drive_link | Open
33 | 27 | check image product-5 | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 5 | NA | functionality,user interface defect | high | high | to display another image page | not to display proper image page, open another image with different name (https://www.saucedemo.com/inventory-item.html?id=3) | Konik | https://drive.google.com/file/d/1eRo-tAZAwXvexWb8Wge-bMdP9H-1w6nV/view?usp=drive_link | Open
34 | 28 | check addtocart button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 5 5) check addto cart button | NA | functionality defect | medium | medium | Not to add image in addtocart page from menu page | add product in cart from menu page but not add product inside the image page but when we go to the add to cart menu the weblink was down/server fail issue | Konik | Page automatic go to redirect | Open
35 | 29 | check remove button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 5 5) check remove button | NA | functionality defect | medium | medium | not remove image from addtocart menu | not remove product from main menu page or inside the image page | Konik | Page automatic go to redirect | Open
36 | 31 | check image product-6 | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 6 | NA | functionality,user interface defect | high | high | to display another image page | not to display proper image page, open another image with different name (https://www.saucedemo.com/inventory-item.html?id=4) | Konik | https://drive.google.com/file/d/1Kr-ykfZeqyUZS4H8_N7S9dtW1Gk_8pVT/view?usp=drive_link | Open
37 | 32 | check addtocart button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 6 5) check addto cart button | NA | functionality defect | medium | medium | Not to add image in addtocart page from menu page | not add product in cart from menu page but add product inside the image page but when we go to the add to cart menu the weblink was down/server fail issue | Konik | Page automatic go to redirect | Open
38 | 33 | check remove button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product - 6 5) check remove button | NA | functionality defect | medium | medium | not remove image from addtocart menu | not remove product from main menu page or inside the image page | Konik | https://drive.google.com/file/d/153WCv5NOej_pmxh5O6i6zux1y2NPC740/view?usp=drive_link | Open
39 | 36 | check checkout information menu with no first name, no last name, no zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for first name) | Konik | https://drive.google.com/file/d/1SAmjWmzGZuZV23sUDZ5vNHxGzFZfcTow/view?usp=drive_link | Open
40 | 36 | check checkout information menu with first name, no last name, no zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for last name) | Konik | https://drive.google.com/file/d/1qbJFOquJe6HS1dXAcOyb0-OgcEMu6Qts/view?usp=drive_link | Open
41 | 36 | check checkout information menu with no first name, last name, no zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for first name) | Konik | https://drive.google.com/file/d/1b6P54TMybWJA8ECp2yzl2Uei48j1uCmg/view?usp=drive_link | Open
42 | 36 | check checkout information menu with no first name, no last name, zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for first name) | Konik | https://drive.google.com/file/d/1VFTl9T5AIyWQqVEdQu2Z8PqX-_WWL5PO/view?usp=drive_link | Open

## perfomance_glitch_user
Defect ID | TestCase ID | Defect Summary | Reproduced Step | Test Data | Defect Type | Defect Priority | Defect Severity | Expected Result | Actual Result | Tester Name | Attachment | Status
1 | 2 | check login button | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : perfomance_glitch_user Password : secret_sauce | Functionality, security defect | high | high | To open the user dashboard with proper details | As Per Expected Resultbut not to see user detail after Login | Konik | https://drive.google.com/file/d/13RvvFXIEAF_kWiQhoSX18X_QBpRnFmZy/view?usp=drive_link | Open
2 | 2 | check login button with blank/null value | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message only show username is required not to show password message | Konik | https://drive.google.com/file/d/1FzXKLYc-8hvQTBwwoLLivPJZ4UjbKh5u/view?usp=drive_link | Open
3 | 2 | check login button with wrong value | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf Password : asdf | Functionality defect | medium | low | To display proper validation message | error message is proper but not to display properly its inside the text box | Konik | https://drive.google.com/file/d/1SQoo1fk0L-puTDA-wkg8_SPS1tulVzoB/view?usp=drive_link | Open
4 | 2 | check login button with username is correct but password is wrong | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : perfomance_glitch_user Password : asdf | Functionality defect | medium | low | To display proper validation message | not to display proper validation message and also not to display proper message insite textbox | Konik | https://drive.google.com/file/d/1DDF8kQXijqPpZP61ARZ7yY2fzv9fAfZF/view?usp=drive_link | Open
5 | 2 | check login button with username is wrong but password is correct | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message and also not to display proper message insite textbox | Konik | https://drive.google.com/file/d/17jWvqmR6cEA_Oa9NH950SK6YDQRyLuZF/view?usp=drive_link | Open
6 | 2 | check login button with proper length in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdfasdfasdfasdfasddaaddaasdf Password : secret_sauce | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1ZNCJPyoGjClp61OfJOH4INx5I2yvn9nG/view?usp=drive_link | Open
7 | 2 | check login button with special character in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : asdf@#$asdf Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1Nf95EL1neOkWW0SHQWZRejUEdHwrT-78/view?usp=drive_link | Open
8 | 2 | check login button with only digit in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : 123456789 Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1NcK2ZCsD3JwOBowD5pWm2iyYQE2z6Wc4/view?usp=drive_link | Open
9 | 2 | check login button with using white space in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : k o n I k Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/115k4AxMdRkE2wH6n_heFftNNln2_u9I4/view?usp=drive_link | Open
10 | 2 | check login button with using white space after and before username in username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : k o n I k Password : | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1_awOj68lt5b-MssOjODTqkeKKErbm1Ym/view?usp=drive_link | Open
11 | 2 | check login button with using white space after and before password in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1T4X8txUkmX_v3ELB_3-wPRDCq54FQmIY/view?usp=drive_link | Open
12 | 2 | check login button with max length of username | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konikkonikkonikkonik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1NyR4DWFvGFy6T9H84i_MTlmTA78CoBjf/view?usp=drive_link | Open
13 | 2 | check login button with not to same username in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1J0Pek56bkOemxIjwNe-1wRYCnBQtp0Wu/view?usp=drive_link | Open
14 | 2 | check login button with uppercase in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : Konik Password : konik | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1Y8WgTcHH9hWTRWPN2TFlsG3wvBWCWSTZ/view?usp=drive_link | Open
15 | 2 | check login button with lowercase in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1p2sSqICQ4-if-cmhQwUDT2IDTYa6YzQD/view?usp=drive_link | Open
16 | 2 | check login button with one digit in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK2711 | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1DBfB4oUJGjK1vHAh10Pwtv-nMGl-gPIW/view?usp=drive_link | Open
17 | 2 | check login button with one special character in password | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button | username : konik Password : KONIK@2711 | Functionality defect | medium | low | To display proper validation message | not to display proper validation message | Konik | https://drive.google.com/file/d/1yRwA579SGCvbW45FpeT3hNcYi3czrltK/view?usp=drive_link | Open
18 | 4 | check all item menu | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) check side menu 5) click allitems menu | Na | Functionality defect | medium | medium | To open items page | no to do anything upon that | Konik | https://drive.google.com/file/d/12r0bHx2C91B4_plnk-IxQISiJW5p8zRq/view?usp=drive_link | Open
19 | 5 | check about menu | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) check side menu 5) click about menu | Na | Functionality defect | low | low | To open the about page | to open another website (https://app.eu-central-1.saucelabs.com) | Konik | https://drive.google.com/file/d/1EZimDBdzCqc5qTl_kphyoMqv_86z2F8L/view?usp=drive_link | Open
20 | 6 | check reset app state | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) check side menu 5) click Reset app state | Na | Functionality defect | low | low | To open the reset app state page | no to do anything upon that | Konik | https://drive.google.com/file/d/1RzHApUODZffUFMhPEOpWkTeLSNsFsJEe/view?usp=drive_link | Open
21 | 19 | check checkout information menu with no first name, no last name, no zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for first name) | Konik | https://drive.google.com/file/d/1SAmjWmzGZuZV23sUDZ5vNHxGzFZfcTow/view?usp=drive_link | Open
22 | 19 | check checkout information menu with first name, no last name, no zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for last name) | Konik | https://drive.google.com/file/d/1qbJFOquJe6HS1dXAcOyb0-OgcEMu6Qts/view?usp=drive_link | Open
23 | 19 | check checkout information menu with no first name, last name, no zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for first name) | Konik | https://drive.google.com/file/d/1b6P54TMybWJA8ECp2yzl2Uei48j1uCmg/view?usp=drive_link | Open
24 | 19 | check checkout information menu with no first name, no last name, zip/postal code | 1) https://www.saucedemo.com 2) Press Enter Key 3) Click on Login Button 4) click on image product 5) check addto cart button 6) click on check out menu | na | Functionality defect,user interface defect | high | high | to open information page of coustomer | to open information page of coustomer but not to display proper message (only show error message for first name) | Konik | https://drive.google.com/file/d/1VFTl9T5AIyWQqVEdQu2Z8PqX-_WWL5PO/view?usp=drive_link | Open